## RAID LOG
| RAID Log | Should you face any difficulty in completing the RAID Log, please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f | [8 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 1 | 0 | 1 | 0 | 0 | 0
| Project title: | LinkedIn-Style Social Media Platform |  | Project Id: | IP-6622 | Project Manager: | Harshada Topale |  |  | Assumption | 1 | 0 | 0 | 0 | 1 | 0
[10 empty] | Issue | 1 | 0 | 0 | 0 | 0 | 0
| DOCUMENT VERSION: | 1 |  | Last Updated date: | 2025-06-28 | Project Team Lead: | ABC |  |  | Dependency | 1 | 0 | 0 | 0 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 4 |  |  |  |  | 2
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | Cloudinary upload may fail due to API quota limits | Image upload may fail; user experience affected | Add error handling and fallback UI for image uploads | Sachit Pandey | High | 6 | Open | Risk
2 | Assumption | MongoDB Atlas will remain available during development | If Atlas becomes unavailable, the project stalls | Chose a stable cloud provider; maintain backups | Sachit Pandey | Low |  | Open | Assumption
3 | Issue | API route mismatch caused 404 errors | App functionality broken; users can't post/connect | Fixed API route paths and ensured consistency | Sachit Pandey | Critical | 9 | Closed | Issue
4 | Dependency | Post creation depends on user authentication and valid token | Posting won’t work without auth; blocks critical flow | Middleware ensures valid tokens before access | Sachit Pandey | Medium |  | Open | Dependency
5
6 | [8 empty] | Open
7 | [8 empty] | Closed
8
9 | [8 empty] | Critical
10 | [8 empty] | High
11 | [8 empty] | Moderate
12 | [8 empty] | Low
13 | [8 empty] | Negligible
14
15
16
17
18
19
20
21
22
23
24